## Slide 1
FEB COMPOSITES · SN6
Prepreg Feasibility
SN6 Wing Endplates
SN5 endplates were 2272 g of flat plate. Here is the plan to fix that.
PFS-001 Rev A · 2026-07-31 · feasibility study + BOM + test deadlines
2 plies carbon · Nomex · 2 plies carbon

## Slide 2
The problem: our flat plates weigh kilograms
2272 g
SN5 rear wing endplate set (P-SN5-008)
glass infusion over 0.25 in Nomex
7 plies rear (WO-SN5-008)
5 plies front (WO-SN5-014)
These were the heaviest simple parts we made.
Glass needs the plies
Glass is roughly a third the stiffness of carbon per ply, so panel stiffness took 7 plies where carbon needs 2 per side.
Infusion resin content is whatever the bag decides
Resin fraction depends on mesh, vacuum quality, and when the line gets clipped. Nobody chose that weight; the process did.
Result: heavy panels, no knob to turn
Staying on glass infusion means SN6 endplates come out the same. Getting lighter needs a process change, not more care.

## Slide 3
The proposal: prepreg skins, cocured to our Nomex, oven cure
Factory-set resin
Prepreg is cloth pre-impregnated with an exact resin content. No mixing, no pot life, no infusion lines, no trap. The panel weighs what the stack math says.
One cure, whole sandwich
Skins cocure straight onto the Nomex core ACP already donated. Vacuum bag only; no autoclave anywhere in this plan.
Heat instead of patience
An oven cures a panel in hours with a logged temperature trace, instead of 14 days to full ambient-cure properties.
35 to 45% estimated saving: 800 to 1000 g off the RW endplate set
Estimates from cloth and core datasheets. Measured test panels supersede them; that is what the fall timeline produces.

## Slide 4
Two material paths
A
Path A: ACP RTS prepreg
198 gsm 2x2 twill carbon, room-temperature storage: no freezer at all
Cure 4 h at 132 °C, vacuum bag + oven
ACP already sponsors us (they donated the Nomex)
They sell expired rolls at clearance: the donation ask is nearly free for them
Long out-life makes the whole schedule slack-tolerant
B
Path B: XPREG XC110
210 gsm 2x2 twill carbon, about $46.49 per yard retail
Cures from 85 °C: a DIY or domestic oven is enough
Needs a freezer (-18 °C) and a 30-day out-time log
Ships from the UK: customs delay risk we already lived through (PP-02)
Supplier we know, but not a sponsor
The coupling: A deletes the freezer question but needs a 132 °C oven. B only needs 85 °C but needs the freezer and beats the out-life clock. We decide Sep 4, after ACP answers and the oven question is settled.

## Slide 5
Will it bond to honeycomb without an autoclave?
Yes, per published studies
Vacuum-bag-only cocure of prepreg skins on Nomex is a documented, workable process, not an experiment we invented.
Our geometry is the easy case
Core crush concentrates at ramped or chamfered core edges. Endplates are flat panels with square-cut core: the classic driver is absent.
Fillets from adhesive film
A layer of XA120 film bonds skin to cell walls. If a with/without coupon shows our prepreg self-adheres, we drop the film and save 300 g/m².
Controls, not hope
Partially vented core per the literature, section cuts on the cocure panel, and the CS-006 drop test carried straight over.
Cocured sandwich, one cure cycle
prepreg skin, 2 plies
Nomex honeycomb 0.25 in ($0, donated)
prepreg skin, 2 plies
gold = resin fillet bond lines. Section cuts on Panel 2 prove the fillets are continuous and the core is not crushed before any car part gets laid up.

## Slide 6
What we need from RFS: the Larry conversation
1. Can we share the CalSol freezer?
Only matters on Path B (XC110). Our discipline rules, written before anyone asks:
Sealed moisture-proof bags only, labeled with date and out-time
Out-time log rides with the roll (30-day budget)
Thaw sealed, so condensation lands on the bag, not the cloth
Never a food fridge. We remember 2026-02-17.
2. What oven can we use?
Path A needs 132 °C, Path B only 85 °C. Options in order:
An oven that already exists at RFS: $0
Dedicated used domestic oven: $50 to 150 (never food again)
DIY insulated PID box sized to the endplate: $200 to 400
Also: footprint and circuit if we bring our own.
BLOCKER either way: no panel cures until an empty-oven thermal survey passes with a logged ramp (~2 °C/min) and dwell inside the datasheet band.

## Slide 7
What we ask sponsors, and why they say yes
ACP Composites
existing sponsor, donated our Nomex core
One expired RTS prepreg roll from their clearance stock
Their clearance page proves the stock exists; expired is fine, we coupon-test first
Near-zero cost to them, a whole new process for us
Same box: a roll of Stretchlon 800 high-temp bag film
Airtech
existing consumables sponsor
High-temperature bagging consumables: film, sealant tape, release, breather
Our infusion film (VB160) is rated 160 °C; cure cycles want real margin
Small-dollar ask, recurring visibility on every cure we run
Both emails out by Aug 14, routed through the lead per CS-012. Draft text is in the study, Appendix A.

## Slide 8
Cost: retail worst case vs sponsored
Item | Retail | Sponsored
Prepreg carbon, ~10 yd² (3 panels + endplate set) | $465 to 1,522 | $0 (ACP expired roll)
XA120 adhesive film, ~3 yd² | $75 | $75
Nomex 0.25 in core, 2 sheets | $0 | $0 (already donated)
High-temp bag film, tape, release, breather | $287 | $0 (Airtech)
Thermocouple logger, 2-ch K-type | $30 to 60 | $30 to 60
Cure oven (Larry conversation decides) | $0 to 400 | $0 to 400
Freezer (Path B only; $0 if CalSol shares) | $180 to 250 | $0
RETAIL, NO SPONSORS
$400 to 900
plus oven $0 to 400. Still a viable pilot.
SPONSORED PATH
$105 to 535
ACP roll + Airtech consumables donated
Go/no-go requires out-of-pocket at or under $500. The sponsored column is how we get there; the retail column is the honest worst case.

## Slide 9
Timeline: decision before the semester ends
Aug 14
Sponsor emails out: ACP (expired roll + Stretchlon), Airtech (consumables)
Aug 21
Larry answers in writing: CalSol freezer, oven
Sep 4
BLOCKER Path A/B chosen, order placed. No order before the decision.
Sep 25
BLOCKER Oven commissioned, empty-oven thermal survey passed. No cure before survey.
Oct 9
Panel 1: flat monolithic prepreg, cure-log review
Oct 30
Panel 2: cocure over Nomex + section cuts for fillets and core crush
Nov 20
Panel 3 pair: prepreg vs SN5-equivalent glass. Weigh + 3-point bend.
Dec 4
BLOCKER GO / NO-GO review with the Lead, recorded as Rev B
Dec 11
If GO: CS-014 scoped, SN6 endplate work order drafted for spring

## Slide 10
Go/no-go criteria, decided Dec 4
≥ 30% lighter
measured per m² against the SN5-equivalent glass panel, same area, same scale
Stiffness holds
3-point-bend stiffness at or above the glass baseline panel
Core survives
no visible core crush; section cuts show continuous resin fillets at the cell walls
Cure is proven
every panel's logged ramp and dwell inside the datasheet band
≤ $500 out of pocket
total pilot spend on the sponsored path
“We decide with a scale and a bend test, not vibes.”
Any criterion failed: NO-GO, reasons recorded, fallback is carbon infusion on the process we already run.

## Slide 11
If this works
CS-014: Prepreg Layup and Oven Cure
a new team standard written from the pilot's own records
SN6 wing skins go prepreg next
the biggest composite mass after the endplates (one more study first: tooling board at cure temp)
Permanent capability
the oven and freezer stay; elevated post-cure stops being aspirational for infusion too
A deeper ACP relationship
from core donor to process sponsor, with clearance stock available every season
The ask this week: approve the two outreach emails. Everything else on the timeline hangs off them.